## Template Retrospective
| Sprint Retrospective | Iteration | Week 4
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a developer and I need my data to be stored in a PostGres database | Connecting the database to the GUI | Nathan | 4 | 4 | Not yet
| I am a developer - I need this in order to be able to communicate with the client | Look into the Spring framework and the RestAPI | Jari | 4 | 4 | Not yet
| I am a developer - I need this in order to be able to communicate with the client | Look into the Spring framework and the RestAPI | Johannes | 4 | 4 | Not yet
| I am a developer - I need this in order to be able to communicate with the client | Look into the Spring framework and the RestAPI | Lukas | 4 | 4 | Not yet
| I am a user and I am interested in an interactive GUI and I need a way to communicate with the client | Testing add acount functionality plus API search | Ardy | 4 | 4 | Yes
| I am a user and I am interested in an interactive and bug-free GUI | Login Screen and the Homescreen | Nick | 4 | 4 | Yes
Main Problems Encountered
| Problem 1 | Merge Request Issues | Problem 2 | Fix the git ignore
| Description | Ardy does not get all the options for merging - could not merge his branch into master. He can not solve the merge conflicts | Description | Everytime Lukas imports a project from us, he has to decide which JDK to use.
| Reaction | Anger, sending messages to Khalid | Reaction | Ignore the .idea folder
Adjustments for next Sprint Plan
We will be using the RESTapi and the Nathan's rapsberry pie for hosting
Adjustements from last week
old adjustments:
what we did with the adjustments: