## Template Retrospective
Sprint Retrospective | Iteration | Week 3
Project | Green Thumb
Group | Group 22
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
I am a developer and I need a place to store my users data | Implementing a PostGres database and translate JSON files to SQL queries | Nathan | 4 | 4
Im a developer and I need to be to make sure that our customers can interact with the GUI | Look into and implement actionlisteners | Jari | 4 | 4
I am a developer - I need this in order to be able to communicate with the client | Look for a second time into the Spring framework and move the code that we have so far into the Spring framework. I will also look for alternatives | Johannes | 4 | 4 | not yet
I am a user and I am interested into how much CO2 I save when doing different actions | Look at all the features and determine how much CO2 our users can save when | Lukas | 4 | 4
I am a user and I am interested in an interactive GUI | Further working on GUI application | Ardy | 4 | 4
I am a user and I am interested in an interactive and bug-free GUI | Furter testing the GUI and also working on the GUI login | Nick | 4 | 4
Main Problems Encountered
Problem 1 | Implementing Spring
Description | When trying to implement the server and the client with the Spring framework, we encountered a lot of problems when trying to expand on the basic tutorial. Particularly, the person responsible for the task could not understand how to get the http communication to work
Reaction
Adjustments for next Sprint Plan
This is the first one so no adjustments yet