## Sheet1
Sprint Backlog | Iteration | Week 7
Project | Green Thumb
Group | Group 22
Amount of hours
Member | 6
Estimated amount of hours | 4 each
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a user and i want to be able to access my co2 score from the internet | raspberry pi server | Jari | Nathan | 4 | C
Im a client and I want to see the result of my investment. Im a developer and I want my code to be robust and clean | final report + final presentation + checkstyle erros + add button in gui | Johannes | Jari | 4 | A
I am a developer and I want my server to be secure and robust | checkstyle serverside | Ardy | Johannes | 4 | C
Im a developer and I want my code to be robust and clean | checkstyle errors + change number of co2 | Nick | Lukas | 4 | A
Im a developer and I want my code to be robust and clean | checkstyle errors + add friend button + create account + change password | Nathan | Ardy | 4 | A
Im a user and Im interested in interacting with a beautiful UI | Make the gui more beautiful | Lukas | Nick | 4 | A