## Backlog Week 2
Sprint Backlog | Iteration | TEMPLATE
Project | Green Thumb
Group | 22
Amount of hours
Member | Ardy, Johannes, Nick, Lukas, Nathan, Jari
Estimated amount of hours | 4 per person
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the OOP lecture | Ardy, Johannes | Nathan, Jari | 4 | A
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the Spring framework | Nick, Lukas | Johannes | 4 | A
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using method from Medium | Nathan, Jari | Nick, Lukas | 4 | A