## Sheet1
| Sprint Retrospective | Iteration | Week 8
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a user and i want to be able to access my co2 score from the internet | raspberry pi server + heroku | Nathan | 4 | 9 | not yet | Server works, not client
| Im a client and I want to see the result of my investment. Im a developer and I want my code to be robust and clean | final report + final presentation + checkstyle errors + Testing | Jari | 4 | 20 | not yet
| I am user and I want to be rewarded for my efforts | Test serverside + achievements | Johannes | 4 |  | not yet
| I am a user and I don’t want my password to be stolen by a hacker | Write tests + hash password | Lukas | 4 | 4 | done
| Im a developer and I want my code to be robust | Testing | Ardy | 4 |  | done
| Im a user and I want my GUI to work like it should | Testing + meal choice clarification + clean up GUI | Nick | 4 |  | partially
Main Problems Encountered
| Problem 1 | Checkstyle missing numbers | Problem 2 | mergerequest with conflicts
| Description | We had a lot of missing number |  | Johannes had to merge something that was way behind which caused many merge conflicts
| Reaction | We tried to fix as much of them as possible |  | he had to change a bunch of files
Adjustments for next Sprint Plan
| Write more tests everywhere. | Fix more checkstyle errors.
Adjustements from last week
old adjustments: | checkstyle
what we did with the adjustments: | Jari fixed a lot of them, but we still have many to go