## Sheet1
| Sprint Retrospective | Iteration | Week 5
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a developer and I need my data to be stored in a PostGres database via hibernate | Connecting the database to the server via hibernate | Nathan | 4 | 4 | Not yet | Postgres was abandoned, migrating to mySQL
| I am a user and I am interested in knowing how much CO2 I save with one vegetarian meal | Create an implementation of the vegetarian meal process and the writing to file class | Jari | 4 | 4 | Not yet
| I am a developer - I need this in order to be able to communicate with the client | Implement a Restful server with a connection to a database via hibernate | Johannes | 4 | 4 | Not yet
| I am a developer - I need this in order to be able to communicate with the server | Look into the RestAPI to create a client, create an implementation of the vegetarian meal process, create an account screen | Lukas | 4 | 4 | Not yet
| I am a user and I am interested in knowing how much CO2 I save with one vegetarian meal | Creating the GUI for the vegetarian meal process and the other features, helping Jari with testing, automating the testing process | Ardy | 4 | 4 | Yes
| I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Nick | 4 | 4 | Yes
Main Problems Encountered
| Problem 1 | Gitlab is messy | Problem 2 | Fixing server on other peoples pc
| Description | We have a lot of unnessary files in our gitlab and a lot of our files aren't in the right place. | Description | Only Johannes had the necessary files installed to run the server.
| Reaction | Cleaning up the repository | Reaction | Installing the software on othe people's pc's
Adjustments for next Sprint Plan
| Only use the new server version and delete the old one. | Migrating from postgres to MySQL | Add more tasks to the scrumboard and clean it up.
Adjustements from last week
old adjustments:
what we did with the adjustments: