## Template Retrospective
| Sprint Retrospective | Iteration | Week 2
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the OOP lecture | Nathan, Jari | 4 | 4 | Yes | We managed to create a working version however we found out that it does not use http so we will abandon this idea
| I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the Spring framework | Johannes | 4 | 4 | Yes | We managed to create a working version however we encountered a number of problems with it
| I am a developer - I need this in order to be able to communicate with the client | Create Webserver using method from Medium | Nick, Lukas | 4 | 4 | No | We abandond this idea as the other solutions worked
Main Problems Encountered
| Problem 1 | Implementing Spring
| Description | When trying to implemnt the server and the client with the Spring framework, we encountered a lot of problems when trying to expand on the basic tutorial
| Reaction | We abandond Spring for this week
Adjustments for next Sprint Plan
This is the first one so no adjustments yet
Adjustements from last week
old adjustments: | there werent any retrospectives from last week
what we did with the adjustments: | there werent any retrospectives from last week