## Sheet1
| Sprint Retrospective | Iteration | Week 6
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a user and I want to reliably get my data | make the hardware work with the software | Nathan | 4 | 4 | not yet
| Im a client and I want to see the result of my investment | final report + final presentation | Jari | 4 | 4 | not yet
| I am a user and I want my buttons to work flawlessly | Make GUI features work | Johannes | 4 | 4 | not yet
| I am a developer and I want my code to be robust and clean | Work on testing and checkstyle | Lukas | 4 | 4 | not yet
| I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Ardy | 4 | 4 | partially | main screen not done yet, log in screen is done
| I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Nick | 4 | 4 | partially | main screen not done yet, log in screen is done
Main Problems Encountered
| Problem 1 | pipelining was difficult to accomplish | Problem 2 | Fixing server on other peoples pc
| Description | Ardy worked on pipelining and it didn't work | Description | Only Johannes had the necessary files installed to run the server.
| Reaction | We fixed it during the meeting | Reaction | Installing the software on othe people's pc's
Adjustments for next Sprint Plan
| Making sure everyone can run the application now | We are trying to finish the app for next week | clean up repository
Adjustements from last week
old adjustments: | Only use the new server version and delete the old one. | Migrating from postgres to MySQL | Add more tasks to the scrumboard and clean it up.
what we did with the adjustments: | Everyone now uses the new version of the server | We now use MySQL and gave up on postgres | The scrumboard now actually shows what we are doing