## Sheet1
| Sprint Retrospective | Iteration | Week 7
| Project | Green Thumb
| Group | Group 22
| User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
| I am a user and i want to be able to access my co2 score from the internet | raspberry pi server | Nathan | 4 | 3 | not yet | First trying to make sure it works on heroku
| Im a client and I want to see the result of my investment. Im a developer and I want my code to be robust and clean | final report + final presentation + checkstyle erros + add button in gui | Jari | 4 | 4 | not yet | Good progress on the report
| I am a developer and I want my server to be secure and robust | checkstyle serverside | Johannes | 4 | 4 | not yet | Did something else
| Im a developer and I want my code to be robust and clean | checkstyle errors + change number of co2 | Lukas | 4 | 4.5 | done
| Im a developer and I want my code to be robust and clean | checkstyle errors + add friend button + create account + change password | Ardy | 4 | 12 | done
| Im a user and Im interested in interacting with a beautiful UI | Make the gui more beautiful | Nick | 4 | 3 | partially | Main screen almost done
Main Problems Encountered
| Problem 1 | Heroku
| Description | Documentation is sparse, code is not executed
| Reaction | Keep trying things
Adjustments for next Sprint Plan
| Write more tests everywhere. | Fix more checkstyle errors.
Adjustements from last week
old adjustments: | Making sure everyone can run the application now | We are trying to finish the app for next week. | Clean up repository
what we did with the adjustments: | done | All main barebone features done. | done