## Template Retrospective
Sprint Retrospective | Iteration | Week 2
Project | Green Thumb
Group | Group 22
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the OOP lecture | Nathan, Jari | 4 | 4 | Yes | We managed to create a working version however we found out that it does not use http so we will abandon this idea
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using the Spring framework | Johannes | 4 | 4 | Yes | We managed to create a working version however we encountered a number of problems with it
I am a developer - I need this in order to be able to communicate with the client | Create Webserver using method from Medium | Nick, Lukas | 4 | 4 | No | We abandond this idea as the other solutions worked
Main Problems Encountered
Problem 1 | Implementing Spring
Description | When trying to implemnt the server and the client with the Spring framework, we encountered a lot of problems when trying to expand on the basic tutorial
Reaction | We abandond Spring for this week
Adjustments for next Sprint Plan
This is the first one so no adjustments yet

## Template Backlog
Sprint Backlog | Iteration | Week 3
Project | Green Thumb
Group | Group 22
Amount of hours
Member | 6
Estimated amount of hours | 4 each
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a developer and I need a place to store my users data | Implementing a PostGres database and translate JSON files to SQL queries | Jari | Nathan | 4 | A
Im a developer and I need to be to make sure that our customers can interact with the GUI | Look into and implement actionlisteners | Johannes | Jari | 4 | A
I am a developer - I need this in order to be able to communicate with the client | Look for a second time into the Spring framework and move the code that we have so far into the Spring framework. I will also look for alternatives | Ardy | Johannes | 4 | A
I am a user and I am interested into how much CO2 I save when doing different actions | Look at all the features and determine how much CO2 our users can save when | Nick | Lukas | 4 | B
I am a user and I am interested in an interactive GUI | Further working on GUI application | Nathan | Ardy | 4 | B
I am a user and I am interested in an interactive and bug-free GUI | Furter testing the GUI and also working on the GUI login | Lukas | Nick | 4 | A