## Template Backlog
Sprint Backlog | Iteration | Week 5
Project | Green Thumb
Group | Group 22
Amount of hours
Member | 6
Estimated amount of hours | 4 each
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a developer and I need my data to be stored in a PostGres database via hibernate | Connecting the database to the server via hibernate | Jari | Nathan | 4 | A
I am a user and I am interested in knowing how much CO2 I save with one vegetarian meal | Create an implementation of the vegetarian meal process and the writing to file class | Johannes | Jari | 4 | A
I am a developer - I need this in order to be able to communicate with the client | Implement a Restful server with a connection to a database via hibernate | Ardy | Johannes | 4 | A
I am a developer - I need this in order to be able to communicate with the server | Look into the RestAPI to create a client, create an implementation of the vegetarian meal process, create an account screen | Nick | Lukas | 4 | B
I am a user and I am interested in knowing how much CO2 I save with one vegetarian meal | Creating the GUI for the vegetarian meal process and the other features, helping Jari with testing, automating the testing process | Nathan | Ardy | 4 | B
I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Lukas | Nick | 4 | A