## Sheet1
Sprint Backlog | Iteration | Week 8
Project | Green Thumb
Group | Group 22
Amount of hours
Member | 6
Estimated amount of hours | 4 each
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a user and i want to be able to access my co2 score from the internet | raspberry pi server/heroku | Jari | Nathan | 4 | A
Im a client and I want to see the result of my investment. Im a developer and I want my code to be robust and clean | final report + final presentation + checkstyle errors + Testing | Johannes | Jari | 4 | A
I am user and I want to be rewarded for my efforts | Test serverside + achievements | Ardy | Johannes | 4 | C
I am a user and I don’t want my password to be stolen by a hacker | Write tests + hash password | Nick | Lukas | 4 | A
Im a developer and I want my code to be robust | Testing | Nathan | Ardy | 4 | A
Im a user and I want my GUI to work like it should | Testing + meal choice clarification + clean up GUI | Lukas | Nick | 4 | A