## Sheet1
Sprint Backlog | Iteration | Week 6
Project | Green Thumb
Group | Group 22
Amount of hours
Member | 6
Estimated amount of hours | 4 each
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
I am a user and I want to reliably get my data | make the hardware work with the software | Jari | Nathan | 4 | A
Im a client and I want to see the result of my investment | final report + final presentation | Johannes | Jari | 4 | C
I am a user and I want my buttons to work flawlessly | Make GUI features work | Ardy | Johannes | 4 | A
I am a developer and I want my code to be robust and clean | Work on testing and checkstyle | Nick | Lukas | 4 | A
I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Nathan | Ardy | 4 | B
I am a user and I am interested in interacting with a beautiful interface | Make the GUI more beautiful | Lukas | Nick | 4 | B